## Tracker
Defect ID | [10 empty] | Date | Feature | Description | Severity | Priority | Reported By | Assigned To | Status | Fix / Resolution | Retest Result
D-01 | 23-Oct | Auth/Isolation | Customer A could access Customer B's ticket by changing the ID in the URL. | Critical | High | Wian | Wian | Closed | Added get_ticket() ownership check on all ticket routes. | Pass
D-02 | 23-Oct | Security | Forms accepted POST requests without a valid CSRF token. | High | High | Wian | Wian | Closed | Added _csrf token validation in before_request. | Pass
D-03 | 24-Oct | Assignment | Assignee field accepted invalid IDs or customers as assignees. | High | Medium | Freek | Wian | Closed | Validated assignee against role='agent' in SQL query. | Pass
D-04 | 24-Oct | Validation | Error messages were generic (e.g., "Invalid input"). | Medium | Low | Freek | Freek | Closed | Rewrote messages to name the field and the fix. | Pass
D-05 | 24-Oct | UI/UX | No confirmation shown after creating a ticket; users missed the list. | Medium | Low | Freek | Freek | Closed | Added a flash message with the ticket ID and a link. | Pass