## Tracker
PROJECT SCHEDULE & SPRINT BACKLOG
Task ID | Chapter/Sprint | Task / User Story | Owner | Start Date | Due Date | Priority | Status | % Complete | Evidence / Deliverable
P01 | Planning | Confirm SmartDesk customer support ticketing project | Freek & Wian | 2026-10-19 | 2026-10-19 | High | Completed | 100 | Project scope and title agreed.
P02 | Planning | Prepare topic proposal and project charter | Freek & Wian | 2026-10-19 | 2026-10-22 | High | Completed | 100 | Topic proposal and charter finalised.
C01 | Chapter 1 | Write introduction, problem statement and objectives | Freek | 2026-10-19 | 2026-10-22 | High | Completed | 100 | Chapter 1 finalised.
C02 | Chapter 2 | Research ticketing solutions and literature review | Wian | 2026-10-19 | 2026-10-22 | High | Completed | 100 | Chapter 2 and literature review matrix finalised.
C03 | Chapter 3 | Define functional and non-functional requirements | Freek & Wian | 2026-10-20 | 2026-10-22 | High | Completed | 100 | Chapter 3 and SRS finalised.
C04 | Chapter 4 | Document architecture, database and implementation | Freek & Wian | 2026-10-20 | 2026-10-23 | High | Completed | 100 | Chapter 4 finalised; diagrams and screenshots inserted.
D01 | Development | Create Flask app and SQLite database | Freek & Wian | 2026-10-20 | 2026-10-22 | Critical | Completed | 100 | Working local Flask app; database initialized.
D02 | Development | Implement login, user roles and access controls | Freek & Wian | 2026-10-20 | 2026-10-22 | Critical | Completed | 100 | Working app; automated access-control test passed.
D03 | Development | Implement ticket creation, viewing and comments | Freek & Wian | 2026-10-20 | 2026-10-22 | Critical | Completed | 100 | Working app; manual checks and pytest passed.
D04 | Development | Implement ticket assignment, status and dashboard | Freek & Wian | 2026-10-20 | 2026-10-22 | Critical | Completed | 100 | 20 manual checks reported passed.
T01 | Testing | Run 20 manual functional checks | Freek | 2026-10-22 | 2026-10-22 | High | Completed | 100 | 20/20 manual checks passed.
T02 | Testing | Run automated pytest suite | Freek | 2026-10-22 | 2026-10-23 | High | Completed | 100 | 3 passed in 0.88s; terminal output.
T03 | Testing | Complete test plan, RTM and defect log | Freek & Wian | 2026-10-22 | 2026-10-23 | High | Completed | 100 | Test plan, RTM, and defect log populated with final evidence.
C05 | Chapter 5 | Write testing, results and evaluation chapter | Freek & Wian | 2026-10-22 | 2026-10-23 | High | Completed | 100 | Chapter 5 finalised with automated test evidence.
C06 | Chapter 6 | Write conclusions and recommendations | Freek & Wian | 2026-10-22 | 2026-10-23 | High | Completed | 100 | Chapter 6 finalised.
V01 | Design | Prepare system architecture, ERD and UML diagrams | Freek & Wian | 2026-10-22 | 2026-10-23 | High | Completed | 100 | Diagrams verified against final app.
E01 | Evidence | Capture application and automated test screenshots | Freek | 2026-10-23 | 2026-10-25 | Critical | Completed | 100 | Dashboard, tickets, assignments, comments, pytest output captured.
E02 | Evidence | Verify actual task ownership, hours and signatures | Freek & Wian | 2026-10-23 | 2026-10-26 | High | Completed | 100 | Attendance register verified and signed by both members.
Q01 | Quality | Test remaining security and validation requirements | Wian | 2026-10-24 | 2026-10-26 | High | Completed | 100 | Test evidence and updated RTM/defect log finalized.
F01 | Final dissertation | Reconcile stack, references and chapter content | Freek & Wian | 2026-10-24 | 2026-10-26 | Critical | Completed | 100 | Flask/SQLite consistent final dissertation.
F02 | Final dissertation | Insert diagrams, screenshots and appendices | Freek & Wian | 2026-10-25 | 2026-10-27 | Critical | Completed | 100 | Final compiled Word dissertation.
S01 | Presentation | Prepare 12-slide presentation and demo script | Wian | 2026-10-25 | 2026-10-27 | High | Completed | 100 | Slides and demo outline complete.
S02 | Presentation | Rehearse demonstration and verify submission files | Freek & Wian | 2026-10-27 | 2026-10-28 | Critical | Completed | 100 | Rehearsal checklist and final QA complete.
S03 | Submission | Submit SmartDesk capstone project | Freek & Wian | 2026-10-29 | 2026-10-29 | Critical | Completed | 100 | Submission receipt / confirmation obtained.

## Project Notes
SMARTDESK — SCHEDULE NOTES
Project | Customer Support Ticketing System
Team | Freek Schaefer-Gerber; Wian Sandenbergh
Lecturer | Dunstan
Submission deadline | 29 October 2026
Progress basis | Reported work and created draft artifacts as of 23 October 2026
Ownership and dates | Proposed allocations / estimated dates; verify with Wian before submission
Status rule | Completed = reported working or verified; Draft complete = document exists but needs review; Pending = not confirmed