## Tracker
PROJECT RISK, ISSUE & CHANGE REGISTER
ID | Type | Date | Description | Likelihood | Impact | Priority | Owner | Mitigation / Action | Status | Due Date | Outcome
R-001 | Risk | 2026-10-19 | Late completion of dissertation evidence and appendices | High | High | Critical | Freek & Wian | Prioritise essential screenshots, diagrams and testing evidence; review daily. | Closed | 2026-10-28 | Evidence and appendices completed and verified.
R-002 | Risk | 2026-10-19 | Insufficient time to prepare and rehearse final demonstration | Medium | High | High | Freek & Wian | Prepare demo script; rehearse core ticket workflows before submission. | Closed | 2026-10-28 | Demo rehearsed successfully with backup plan prepared.
R-003 | Risk | 2026-10-20 | Loss of project files or SQLite database during editing | Medium | High | High | Freek & Wian | Maintain backups of source, database and documents; use version control. | Closed | 2026-10-28 | Git repository and local backups verified.
R-004 | Risk | 2026-10-22 | Dissertation technology descriptions differ from implemented Flask/SQLite stack | High | Medium | High | Freek & Wian | Update Chapters 3–6 to reflect actual implementation and database. | Closed | 2026-10-27 | Chapters 3-6 updated to reflect actual tech stack.
R-005 | Risk | 2026-10-22 | Automated tests do not cover all system functions and security scenarios | High | Medium | High | Wian Sandenbergh | Extend test coverage; retain untested requirements as pending in RTM. | Closed | 2026-10-27 | 3 automated and 20 manual tests passed; RTM updated.
R-006 | Risk | 2026-10-23 | Unverified attendance times, student numbers and task ownership | Medium | Medium | Medium | Freek & Wian | Verify register against actual attendance and contributions; obtain signatures. | Closed | 2026-10-28 | Attendance register verified and signed.
I-001 | Issue | 2026-10-22 | PowerShell execution policy blocked virtual environment activation | N/A | Low | Low | Freek Schaefer-Gerber | Run .venv Python executable directly without changing system execution policy. | Resolved | 2026-10-22 | Flask app started successfully via workaround.
I-002 | Issue | 2026-10-22 | Initial Python package installation ran outside virtual environment | N/A | Medium | Medium | Freek Schaefer-Gerber | Install dependencies with .venv\Scripts\python.exe -m pip install -r requirements.txt. | Resolved | 2026-10-27 | Subsequent pytest ran successfully using .venv Python.
C-001 | Change | 2026-10-22 | Use Flask and SQLite for working prototype rather than earlier proposed React/ASP.NET/SQL Server | N/A | High | High | Freek & Wian | Align dissertation, diagrams and demonstration with implemented stack. | Implemented | 2026-10-27 | Dissertation and code accurately reflect the Flask/SQLite implementation.
C-002 | Change | 2026-10-23 | Add automated pytest results to Chapter 5 and requirements evidence | N/A | Medium | Medium | Freek & Wian | Document 3 passed tests and attach screenshot of terminal output. | Completed | 2026-10-27 | Automated test results and screenshots included in Chapter 5 and Appendices.